## Risk Register
ID | Category | Description | Task(s) | Vendor Related | Prob. Level | Impact Level | Score | Band | Impact (days) | Impact (cost) | Response | Mitigation | Owner | Trigger
R6 | External | Jet fuel price volatility invalidates opex assumptions after the budget is locked, since fuel is 28% of operating cost. | T2.2, T5.2 |  | 4 | 4 | 16 | Critical | 0 | 15000 | Mitigate | Build the fuel sensitivity model (T5.2) before, not after, budget sign-off; keep a fuel hedge/contingency line visible in the rolling forecast. | Finance Lead | Fuel forward curve moves >10% from the budgeted assumption in any month.
R1 | Vendor | OAG Aviation Data schedule/fleet feed delivery slips past the need date, delaying the whole data foundation phase. | T1.2 | Yes | 3 | 4 | 12 | High | 8 | 6000 | Mitigate | Confirm data delivery SLA in writing before kickoff; request a sample extract in week 1 to de-risk format issues. | Data Analyst | No confirmed delivery date from OAG by day 2 of T1.2.
R2 | Vendor | Platts fuel price feed contract signing slips, delaying the fuel scenario model that underpins 28% of opex. | T5.1, T5.2 | Yes | 3 | 4 | 12 | High | 6 | 8000 | Mitigate | Start Platts contracting in parallel with T2.2, not after; keep Refinitiv identified as a backup feed. | Data Analyst | Contract unsigned 5 working days before T5.1 start.
R7 | Cost | Year-1 revenue assumptions ($120M, 82% load factor) are aggressive for a startup airline's first year and may not hold. | T2.1 |  | 3 | 4 | 12 | High | 0 | 12000 | Escalate | Present the revenue model with explicit sensitivity bands (load factor 75/82/88%) to the board rather than a single point estimate. | Finance Lead | Actual load factor in first reporting month is >5pts below 82% target.
R8 | Schedule | This chain of tasks is the critical path; any slip on any one of them pushes go-live day-for-day with zero slack. | T2.2, T2.4, T3.2, T6.1, T7.1, T8.1, T8.2, T10.2, T11.1, T11.2, T11.3 |  | 3 | 3 | 9 | Medium | 5 | 5000 | Mitigate | Weekly critical-path review in Asana; protect these tasks from resource contention with other workstreams. | PM | Any critical-path task shows <50% progress at its midpoint checkpoint.
R10 | Stakeholder | Finance team UAT surfaces late requirement changes to KPI definitions, re-opening upstream model work close to go-live. | T11.2 |  | 3 | 3 | 9 | Medium | 4 | 3500 | Mitigate | Freeze KPI taxonomy (T1.1) formally and require sign-off before T2.1 starts; treat later changes as a change request. | Finance Lead | UAT feedback requests a KPI definition change not in the frozen taxonomy.
R3 | Vendor | Anthropic API rate limits or an account/config issue block the AI variance-commentary integration on first use. | T8.2 | Yes | 2 | 3 | 6 | Medium | 4 | 3000 | Mitigate | Provision API access and run a smoke test during T8.1, not at the start of T8.2. | AI/Automation Engineer | API smoke test fails or returns errors during T8.1.
R4 | Vendor | Power BI licensing/provisioning delay blocks executive dashboard build. | T9.1 | Yes | 2 | 3 | 6 | Medium | 3 | 2000 | Mitigate | Request Power BI Pro licenses for the BI Developer at project kickoff, not at T9.1 start. | PM | Licenses not provisioned 1 week before T9.1.
R5 | Vendor | Slack API/workspace admin approval for automation bots is delayed by IT/security review. | T10.2 | Yes | 3 | 2 | 6 | Medium | 2 | 1000 | Mitigate | Submit Slack app/bot approval request in week 1 alongside T1.3. | AI/Automation Engineer | No IT approval by start of T10.2.
R9 | Resource | Workforce planning depends on a single Finance Analyst; if unavailable, the cash flow forecast (T7.1) is blocked since it has zero slack. | T6.1 |  | 2 | 3 | 6 | Medium | 5 | 4000 | Mitigate | Cross-train a second analyst on the headcount model during T6.1. | Finance Lead | Primary analyst unavailable >2 days during T6.1.

## Summary
Risk Summary
Total risks | 10
Critical risks | 1
High risks | 3
Medium risks | 6
Low risks | 0
Total expected cost exposure (Σ prob x impact_cost) | 30950